## Check List
| Dan Santich Memorial Giant Scale |  |  | Event Start Date | Event End Date
|  |  |  | 2015-10-09 | 2015-10-11
| Action Item | Due Date | Assigned to | Date completed
1 | Club approval | Feb Meeting
2 | Submit Sanction application | 2015-06-11
3 | Produce Flyer | 2015-06-21
4 | Submit Ads to AMA | 2015-07-01
5 | Request raffle donations in writing | 2015-08-15
6 | Get volunteer commitments | 2015-08-10
7 | Arrange for Heli Deli personnel | 2015-08-10
8 | Distribute flyers at other events | 2015-08-25
9 | Distribute flyers to hobby shops | 2015-08-25
10 | Arrange for event MC and PA system | 2015-09-09
11 | Arrange for port-a-johns | 2015-09-24
12 | Check Generator fuel | 2015-09-24
13 | Arrange for trash removal | 2015-09-27
14 | Confirm Heli Deli personnel | 2015-10-02
15 | Arrange for field clean-up and mowing | 2015-10-02
16 | Collect raffle prizes | 2015-10-05
17 | Print AMA paperwork | 2015-10-06
18 | Check field condition and rectify problems* | 2015-10-07
19 | Get seed money and cash box | 2015-10-07
20 | Put out road signs | 2015-10-07
21 | Put up pilot stations and trash barrels | 2015-10-08
22 | Put up Banners | 2015-10-08
23 | Enjoy Event | 2015-10-08
24 | Remove pilot stations | 2015-10-11
25 | Gather Trash and put up cans | 2015-10-11
26 | Receipts to Treasurer | 2015-10-11
27 | Send Forms to AMA | 2015-10-16
28 | Print volunteer vouchers | 2015-10-16
*Check field condition and rectify problems:
Check for wasps
Condition of Heli-Deli
Trim weeds
Toilet paper
Trash bags & trash barrels

## Instructions
Instructions for using the RAMS CD Checklist
1 | Change the name of the event, start date and end date in the appropriate cells
2 | All dates will be adjusted based on the start and end dates.
3 | You may insert or delete tasks. If you insert tasks, you may enter the date for completion of the task or an offset from the start or end dates (see one of the existing task dates for the format)
4 | Be sure and enter the Assigned To person after getting a commitment from that person for the date